## Slide 1: Financial Stabilization Implementation Plan: Protecting Equity, Maintaining Local Control, and Prioritizing Students
1
1
1
3rd Progress Report to the Board of Education and Community
February 11, 2026

## Slide 2: Your Leadership Team Leading Oakland's Fiscal Stabilization and Operational Excellence
2
2
2
Jennifer Brouhard • President, D2
Valarie Bachelor • Vice President, D6
Rachel Latta • D1
VanCedric Williams • D3
Mike Hutchinson • D4
Patrice Berry • D5
Dr. Clifford Thompson • D7
Board of Education Senior Leadership Team
Dr. Sondra Aguilera • Chief Academic Officer
Tara Gard • Chief Talent Officer
Jenine Lindsey • General Counsel
Dr. V. Lynette McElhaney • Chief of Staff
Ryan Nguyen • Chief Financial Officer
Curtiss Sarikey • Chief Partnership Officer
Preston Thomas • Chief Systems & Services Officer
Dr. Denise G. Saddler
Superintendent

## Slide 3: 1. The Challenge
3
Agenda
3
Our Response
Implementation Results
Timeline
Board Ask

## Slide 4: 01 The Challenge - RECAP
4

## Slide 5: The Challenge: Revenue
5
5
REVENUES ARE DOWN
Declining enrollment (34,000 students vs. 37,000+ historically)
Federal COVID relief funds expired
One-time grants sunsetting
Federal uncertainties

## Slide 6: The Challenge: Costs
5
6
COSTS ARE RISING
Health insurance premiums increasing 8-10% annually
Aging facilities requiring emergency repairs
Education costs growing faster than enrollment
Pension contributions (CalSTRS/CalPERS) mandated increases

## Slide 7: The Challenge
5
7
THE RESULT: STRUCTURAL DEFICIT
$100M+ gap between ongoing revenues and ongoing expenses
This isn't a one-year problem we can "wait out"—it's a structural mismatch requiring comprehensive acWon.

## Slide 8: 02 Our Response (Solutions)
8

## Slide 9: The Board’s Mandate
9
9
Resolution No 2526-0177A - Dec. 10, 2025 ” Board Resolution
It is the Board’s duty to approve a fiscally responsible budget preserves local control.
✦ 2025-26. Ensure the Board-required 3% Reserve for Economic Uncertainty is maintained beginning 2025-26 (~$27M total)
✦ 2026-27+. Address projected Unrestricted General Fund deficits over $70M in each of 2026-27 and 2027-28
✦ No school closures
✦ Prioritize reductions in Central, furthest from students
✦ Enhance efforts to improve student attendance and enrollment
✦ Reduce reliance on one-time funds
✦ Improve fiscal controls, monitoring, and transparency
* The Board Resolution (as amended November 19, 2025 contained other directives regarding the Board’s intent and methods to be considered in building budget scenarios.
Financial Goals
Operational Goals

## Slide 10: A Strategic, Four-Phase Approach
10
10
Proactive and Systematic Stewardship
Phase 1: Immediate Stabilization (Winter 2025 - Spring 2026)
Board-initiated third-party verification • Restored reserves • Qualified First Interim
▶ Phase 2: Workforce Realignment (February/March 2026)
Strategic staffing adjustments protecting student-facing services while right-sizing to enrollment reality; Implementing immediate reductions while protecting key programs, maintaining neighborhood schools, and sustaining educational quality
▶ Phase 3: Budget Adoption for FY 26-27 (April-June 2026)
Continued refinement of assumptions, may revise, adopting a balanced budget by June 30
→ Phase 4: Long-Term Sustainability and Growth (FY 27/28 - FY 30/31)
Implementing fiscal expert recommendations • Building operational excellence • Positioning Oakland for enrollment growth and academic achievement gains
The March 15 RIF deadline requires immediate action.
These actions precede a proposed strategic redesign of OUSD - with community and stakeholder engagement for Oakland's educational future.

## Slide 11: 3) Implementation: Reductions to Date
11

## Slide 12: Implementation Plan Overview 2026-27
12
Summarized Actions for 26-27 | Target | Status
Central Office Reductions | $21,000,000 | On Track
School Site Budget Reduction between 7.5-10% | $32,000,000 | Pending
Central Office Reductions 15-20% reduction above 21M | $11,000,000 | On Track
Reduce school site access to unutilized spaces | $1,600,000 | On Track
After budget development second tier contract review | TBD | On Track
Decreased RRMA expenditures | $1,000,000 | On Track
Increased attendance by 2% | $10,000,000 | Under Review
TK Hub Launch for 2-3 Hubs | $1,500,000 | On Track
Centralized Procurement of Materials and Services | TBD | On Track
Fleet Management System (Future Savings) | TBD | On Track
Shift Attendance Specialist & Noon Supervisors to S&C | $3,860,000 | Completed
Shift costs of small schools into S&C | $8,500,000 | Completed
10% reduction of contribution to Special Education | $12,000,000 | Under Review
Feasibility Study for NPS in OUSD Properties | TBD | On Track
Grand Total | $102,460,000 | 

## Slide 13: A) Central Office Reductions
13
Summarized Actions for 26-27 | Target | Status
Central Office Reductions (Click Link To View) | $21,000,000 | On Track
To stabilize our District's finances while protecting classroom resources, SLT conducted a thorough review of central office and operational departments.
This comprehensive analysis identified opportunities to eliminate duplication, consolidate administrative functions, and operate more efficiently.
We prioritized voluntary separations through early retirement incentives to minimize involuntary layoffs and honor staff contributions.
Result: Reduction of approximately 201 FTE central office funded positions —including voluntary early retirements—redirecting resources toward direct student services and reducing General Fund impacts.

## Slide 18: B) Reduce school site access to unutilized spaces
14
Summarized Actions for 26-27 | Target | Status
Reduce school site access to unutilized spaces | $1,600,000 | On Track
Declining enrollment means empty classrooms and unused facilities across our school sites.
We are consolidating operations within buildings—closing underutilized spaces to reduce utility, maintenance, custodial, and security costs.
Site leaders and facilities staff are partnering to identify which areas to close without impacting classroom instruction or student programs.
Result: $1.6 million in operational savings, concentrating resources where students learn every day.

## Slide 19: C) Decrease RRMA Expenditures
15
Summarized Actions for 26-27 | Target | Status
Decreased RRMA expenditures | $1,000,000 | On Track
We are prioritizing Routine Restricted Maintenance Account (RRMA) spending on essential health, safety, and compliance needs only.
By deferring non-critical projects and coordinating maintenance more strategically across sites, we reduce discretionary spending while protecting safe, functional learning environments.
Result: $1 million in maintenance cost reductions without compromising student or staff safety.

## Slide 20: D) TK Hub Launch for 2 – 3 Hubs
16
Summarized Actions for 26-27 | Target | Status
TK Hub Launch for 2 – 3 Hubs | $1,500,000 | On Track
Consolidate Transitional Kindergarten classrooms into 2-3 regional hubs rather than operating small, under-enrolled sections across multiple campuses.
Reduce duplicate staffing and operational costs while maximizing state early learning funding tied to full enrollment.
Improve program quality through shared specialized staff, consistent scheduling, and stronger support systems.
Result: $1.5 million in savings while strengthening TK programming for our youngest learners.

## Slide 21: E) 10% REDUCTION TO SPECIAL EDUCATION
17
Summarized Actions for 26-27 | Target | Status
10% Reduction to Special Education | $12,000,000 | UNDER REVIEW
Proposed $12 million savings
Currently under review to ensure full compliance with federal and state special education law while maintaining all mandated services for students with disabilities.
Analyzing cost drivers across placements, related services, transportation, and third-party contracts—identifying opportunities to shift toward in-district supports and improved service coordination without reducing legally required services.
Joint leadership effort: Special Education leadership, fiscal services, and labor partners are conducting this review.
Once the legal and educational analysis is complete, staff will bring back options.

## Slide 22: F) Feasibility of Non Public School in OUSD
18
Summarized Actions for 26-27 | Target | Status
Feasibility of NPS (Spring 26) | TBD | On Track
RFP for NPS
The District is developing a Request for Proposals (RFP) to determine the feasibility of operating a Non-Public School on an OUSD campus allowing us to serve disabled students currently placed in costly external programs within our own facilities. Anticipated release: Feb/March 2026

## Slide 23: Building Sustainable Educational Excellence for Oakland
19
What Our Students Deserve
When we achieve fiscal stability, Oakland students gain:
Teachers who build careers here, not just survive year to year
Schools focused on learning, not lurching from crisis to crisis
Programs that exist next year and the year after—predictability matters
A district that works for them
Excellence is their birthright. Sustainability makes it possible.

## Slide 24: Our Approach
19
Protect students first: All neighborhood schools remain open, core academic programs protected
Shared sacrifice: Reductions across all divisions and employee groups, leadership takes cuts first
Transparency and partnership: Clear communication, stakeholder engagement, dignified support for affected employees

## Slide 25: Our Core Commitments
19
Fiscal sustainability that enables educational excellence
When finances are stable, schools focus on teaching and learning
Competitive compensation grounded in fiscal reality
Fair pay and sustainable budgets that honor commitments year after year
Operational stability that earns family confidence
Strong financial management demonstrates Oakland is well-governed and worthy of trust
Partnership that solves problems together
Labor, Students, Community, Board, and County working as allies
Excellence as the standard, not the exception
Every Oakland student deserves outstanding education - we accept nothing less

## Slide 26: LABOR PARTNERSHIP Shared Challenge, Shared Solutions
19
Our Commitment to Our Team
OUSD aspires to be an employer of choice:
  Competitive compensation that attracts and retains excellent educators
  Quality working conditions that support professional success
  Professional respect and partnership in problem-solving
  Career development opportunities and pathways for growth
Dignified treatment during transitions

## Slide 27: Support for Affected Employees
19
OUSD CARES:
Comprehensive transition support services
Career counseling, job search assistance, job fair and connections to other opportunities
Clear, timely communication about status and resources
Recognition and appreciation for years of service to Oakland students

## Slide 28: 06 Next Steps
24

## Slide 29: 2025-26 Budget Development and Prioritization Timeline
November - December 2025 First Interim Report Board Adoption of Budget Scenario 3
January 20, 2026 Presentation of the Fiscal Expert Team
(HYA)
October - November 2025
Board Provides Direction on Budget Priorities
January 28, 2026 Update to BOE on Scenario 3 Implementation
December 10, 2026
School Site One Pagers
All Labor Meeting
January-February 25, 2026
Engagement Sessions
Jan 28 All Labor
Feb 5th Budget & Finance Jan 31st PSAC Fish Bowl
February 11, 2026 Board Reviews Budget Reduction Proposals
February 25, 2026 Board takes Action on Reduction in Force
June 2026 Board Adopts 2026-27
LCAP & Budget
May 2026
Governor’s Budget Revise
2026-27 LCAP &
Budget Public Hearing
March 2026 Second Interim Report & March 15th
Reduction Notices
25

## Slide 30: THANK YOU Questions?
26